## 2015 US
Class Reg Sent | reported Rev Rec | Credits | Customer | SO | Status | Date Booked | Ship Date | Internal Planning Meeting | Customer Kick off Meeting | OnSite Start Date | OnSite End Date | Release for Rev Rec | Wait Time | Booked to Kick off | Days to close | $$ SO Amount | Notes | Location | Region | Model Grp | Service | Account Team | Remote | Onsite | Equiptment List Quick View | Shadow | Wait Time | Model Grp | Status | Region
| ü | 190 | State of Co, Judicial | 5673907 | Complete | 2014-09-08 |  |  | 2014-09-18 | 2014-01-08 | 2014-01-16 | 2015-01-20 | Standard | 10 | 134 | 19000 |  | CO |  | WLAN | [6 empty] | Shipping | VPM | Proposed | US
|  | 250 | Cisco ¦ Ingram Micro | 5662175 | Scheduled | 2014-07-17 | 2014-12-01 | 2014-08-14 | 2014-08-14 | 2014-09-30 |  |  | Customer | 28 | -41837 | 25500 | check in with Ronnie and Jon |  | other | VPM | [6 empty] | Standard |  | Booked
| ü | HI HOLD | AG Interactive ¦ American Greetings | 5688734 | Complete | 2014-10-31 |  |  | 2014-10-27 | 2014-11-11 | 2015-02-23 | 2015-02-23 | Standard | -4 | 115 | 9960 |  |  |  | WLAN |  |  | Chris G |  |  |  | Customer | PNA | Scheduled | EMEA
NA | NA | HI HOLD | AT&T CORPORATION Cushman Wakefield | 5668150 | Complete | 2014-08-13 | 2014-12-01 | 2014-08-29 | 2014-09-22 | 2014-12-01 | 2015-03-30 | 2015-04-02 | Customer | 40 | 232 | 11050 | in process HK upgraded, UK upgraded, US needs cabeling 2/20: all CW open items cleared, HK on 2/25 w/Cindy, then Dennis will be back on next week | remote | US | VPM | QS Remote |  | Dennis | na |  |  | Resource | CSN | Complete | AsiaPac
| ü | 220 | XO communications | 5676180 | Complete | 2014-09-16 |  | 2014-09-22 | 2014-09-22 | 2015-01-12 | 2015-01-14 | 2015-01-15 | Standard | 6 | 121 | 22000 |  |  | US | VPM |  |  | Chris G |  |  |  |  | WLAN | In Process | other
| ü | 75 | Baptist Medical | 5702170 | Complete | 2014-12-19 |  |  | 2015-01-19 | 2015-01-19 | 2015-01-22 | 2015-02-05 | Standard | 31 | 48 | 7500 | 12/19: Sent Proposal report closure |  |  | WLAN | Network/Traffic Analysis | Dana David P | Chris G |  |  |  |  | ASPRO | R&D Support
2015-02-05 | ü | 180 | NASSAU COUNTY NY | 5697915 | Complete | 2014-12-10 |  | 2014-12-12 | 2014-12-15 | 2015-01-20 | 2015-01-23 | 2015-01-23 | Standard | 5 | 44 | 18000 | 1/27; sent registration Ongoing remote support | NY | US | VPM | QS OS | Kevin A Ed Canfield Carl H | Cindy | Paul J |  |  |  |  | Post support
2015-02-06 | ü | 180 | Dechert | 5698248 | Complete | 2014-12-11 |  | 2014-12-12 | 2014-12-16 | 2015-01-27 | 2015-01-30 | 2015-01-31 | Standard | 5 | 51 | 18000 | 1/27; sent registration Ongoing remote support | Il | US | VPM | QS OS | Kevin A Carl H | Cindy Sam O | Paul J
| ü | 180 | ASPEN INSURANCE US SERVICES INC | 30674393 | R&D Support | 2014-12-04 |  | 2015-01-05 | 2015-01-14 | 2015-02-03 | 2015-02-05 | 2015-03-02 | Standard | 41 | 88 | 18000 | 2/5: Frank/RD involvement - Active Directory Server issue 2/12: sent out registration QS complete w/ongoing R&D support through Frank |  | US | VPM | QS OS | Ed Canfield | Alan Fogerty | Paul J | continued R&D support
private | ü | 180 | ACXIOM CORPORATION | 5700758 | Complete | 2014-12-23 |  | 2015-01-05 | 2015-01-05 | 2015-02-03 | 2015-02-05 | 2015-03-02 | Standard | 13 | 69 | 18000 | WS complete, waiting PO for TV OS class |  | US | VPM | QS OS | David P Carl H Kevin | Brent | Brent Sam O
NA | ü | HI HOLD Mlanevil | FCCI Services | 5699861 5699871CR | Complete | 2014-12-19 |  | 2014-11-12 | 2015-01-15 | 2015-02-10 | 2015-02-12 | 2015-03-02 | Shipping | 27 | 73 | 18000 | customer ordering Dell equiptment, proposed wk 2/9 and 3/23. Follow up on Friday 1/16 1/19: Overnight TVC. Need to confirm delivery and set up send out registration | Fla | US | VPM | QS OS | Adam Jason | Dennis | Dennis
2015-03-23 | ü | 180 | SCOTTSDALE HEALTHCARE INGRAM | 5687353 & 5687357 | Complete | 2014-10-25 |  | 2015-01-05 | 2015-01-14 | 2015-02-17 | 2015-02-20 | 2015-03-02 | Customer | 81 | 128 | 18000 | 1/5: requested KO call 1/12: mike sent follow up 2/6: check in on deliverables | AZ | US | VPM | QS OS | Mike Jett Trish Gundy | Brent Sam O | Paul J
| ü | 75 | Serta Simmons | 5712277 | Complete | 2015-02-20 |  | 2015-02-15 | 2015-02-16 | 2015-02-19 | 2015-02-27 | 2015-03-02 | Standard | -4 | 10 | 7500 | Douglas quoted - survey, audit, remediation report, and travel. Lisa will schedule a report review 2/19: close out call scheduled for 2/27 released |  |  | WLAN | 1-day | Douglas Jones
|  | 130 | BERKLEY TECHNOLOGY SERVICES (Phase II) | 5700446 | In Process | 2014-12-22 |  | 2015-01-10 | 2015-01-14 | 2015-02-23 |  | 2015-03-04 | Standard | 23 | 72 | 13000 | Frank to update Project Plan accordingly 1/14: Frank set up a webex for 1/22 start 2/9: FranK will get started week of 2/23 | remote | US | VPM | QS Remote | Carl Kevin | Frank | na
|  | HI HOLD | STATE OF NEW YORK, Courts Anixter | 5700991 | In Process | 2014-12-26 | 2015-01-16 |  | 2015-02-10 | 2015-02-23 |  |  | Standard | 46 | -41999 | 15000 | 1/6: sent shipping info 2/9: FranK will get started week of 2/23 | remote | US | VPM | QS Remote | Carl Kevin | Frank | na
| ü | 160 | COMPUCOM SYSTEMS INC Hertz | 5700749 | Complete | 2014-12-23 |  |  |  | 2015-02-23 | 2015-03-15 |  | Standard | -41996 | -41996 |  | 1/12: KO call, have tentative dates. Will follow up on 1/15 1/16: left VM for customer to confirm today date Feb 9 or 16 for survey or loose close out | OK | US | WLAN | Site Survey | Chris Wilson
2015-03-31 |  | 150 | JOSTENS iNGRAM | 5706886 | In Process | 2015-01-22 | 2015-01-28 |  | 2015-02-13 | 2015-02-23 |  |  | Standard | 22 | -42026 | 15000 | customer contacted us, ready to get started. Sent video 2/23 webex 1 2/27 webex 2 3/16: requested update 3/23: requested update 3/24: should close this week, Sam will update with project plan | MI | US | VPM | QS Remote | GeoffreyPaul Stephen Davis | Sam O | NA
|  | HI HOLD | Cenovus ¦ Empowered Networks | TF117643-7-731150 | Complete | 2014-11-16 |  | 2014-11-12 | 2014-11-13 | 2015-02-24 | 2015-02-26 | 2015-02-27 | Customer | -3 | 103 |  |  | Calgary, Alberta | Canada | VPM | QS OS | Arne | Brent | Paul J
|  |  | Owens & Minor |  | Complete |  |  |  |  | 2015-02-25 |  |  |  | 0 | 0 |  | 2/17: 50+ASE's. Emailed Robert for PO or SO# still not clear if they purchased services. Barry T and Paul Z will support 2/23: customer did not include services with initial PO, account team is working with the customer 2/27: Working with Paul Z he was able to get the customers TVC up and running. At this time, that was all the customer was asking for. We did discuss upgrade paths for their ASE’s but they could not provide any info on a plan for this today. |  | US | VPM | ASE Installation | Kevin Carl Robert Holly
2015-03-23 | ü | 110 | PROGRESS FINANCIAL Ingram | 5694074 5694072 | Complete | 2014-11-21 |  | 2015-01-10 | 2015-01-13 | 2015-03-03 | 2015-03-06 | 2015-03-09 | Customer | 53 | 108 | 11000 | date tentative: confirm on 1/29 1/30 Confirmed | CA | US | VPM | QS OS | Ronnie John Giles | Sheldon Sam O | Paul J
2015-03-26 | ü | 150 | SEMCO ENERGY GAS COMPANY INGRAM MICRO | 5700365 | Complete | 2014-12-22 |  | 2015-02-17 | 2015-02-17 | 2015-03-09 | 2015-03-12 | 2015-03-12 | Resource | 57 | 80 | 15000 | TV4400 -consider onste. have not gotten started on this yet, will contact the customer this week (2/12) Webex 1 is scheduled for 3/9 | MARYSVILLE MI | US | VPM | QS Remote | Stephen Davis David Parker | Jerome | NA
2015-03-23 | ü | 180 | TRANSFIRST LLC | 5699403 | Complete | 2014-12-16 |  |  | 2015-01-14 | 2015-03-10 | 2015-03-13 | 2015-03-27 | Resource | 29 | 101 | 18000 | 2/23: customer was non responsive, until today. Requested a delay, but decided to keep the 3/10 date when the next avail was May. Follow up tomorrow 2/25 with deliverables request 3/18: Sent Project completion form (3/27 close out) 3/23: sent registration | CO | US | VPM | QS OS | Mike Jett Trish Gundy | Sam O | Paul J
| ü |  | Bob - government | 5720155 | Complete |  |  |  |  | 2015-03-16 | 2015-03-20 | 2015-04-02 |  |  |  |  | AME 5 day training 2/18: checked with Steph for a PO |  |  | WLAN |  | Stephanie Walker
NA | ü | 150 | GEORGIA COLLEGE | 5714231 | Complete | 2015-02-12 |  |  | 2015-02-20 | 2015-03-16 | 2015-03-20 | 2015-03-26 | Standard | 8 | 42 | 15000 | Lisa will condirm the date and schedule a KO call confirmed, good to go |  |  | WLAN |  | Lavonne
2015-03-26 | ü | 180 | CARDTRONICS | 5696285 | Post support | 2014-12-02 |  | 2015-01-09 | 2015-01-29 | 2015-03-17 | 2015-03-23 | 2015-03-26 | Resource | 58 | 114 | 18000 | 1/12: sent request for KO call no reply NEED TO FOLLOW UP 1/31: webex schedule, will follow up with onsite resource and date 3/17-3/19 2/6: deliverables due, reminder sent 2/26: Ready for Dennis onsite 3/23: waiting for the final project plan to close out | TX | US | VPM | QS OS | Matt Marchbanks Bill Wells | Paul Z | Dennis
|  | 180 | ADP Ingram | 5696340 | Scheduled | 2014-12-10 |  |  |  | 2015-05-11 | 2015-05-15 |  | Standard | -41983 | -41983 |  | AIRMAGNET WIFI ANALYZER & SURVEY BUNDLE Scott will have call w/customer 1/26: discovery call 2/11: Lisa: DCW, kick off call and confirm date Lisa will call to confirm dates, and set up kick off call early March 3/11: check in with the customer sent, looking to schedule 3/23: customer responded, working to determine dates | NJ | US | WLAN | OJT? | Jorge Valez
2015-04-02 | ü | 180 | LOCKHEED KY | 5699776 | Complete | 2014-12-19 |  |  | 2015-01-16 | 2015-03-24 | 2015-03-27 | 2015-04-02 | Resource | 28 | 104 | 18000 | Frank in process 3/25: Jasina on site… | Kentucky | US | VPM | QS OS | Trey O'Banion David P | Frank | Paul J | [5 empty] | S. America
NA | NA | HI HOLD | Avis Budget Group presidio | 5699872 | Complete | 2014-12-19 | 2015-01-20 | 2015-01-20 | 2015-01-23 | 2015-03-24 | 2015-03-27 | 2015-04-02 | Customer | 35 | 104 | 18000 | taps ship 1/20 1/16: requested KO call wk 1/20 - waiting for customer reply Dennis will modify the PP 1/23: customer will confirm 3/24 or 3/31 2/2: locked in - sent updated Project Plan for approval | NJ | US | VPM | QS OS | Carl Kevin | Dennis | Dennis
2015-04-02 | ü | 180 | REPUBLIC NATIONAL DISTRIBUTING CO LLC | 5699882 | Complete | 2014-12-19 |  | 2015-01-16 | 2015-01-16 | 2015-03-30 | 2015-03-31 | 2015-04-02 | Resource | 28 | 104 | 18000 | 1/12: requested KO call | Atlanta | US | VPM | QS OS | Douglas Jones Jason C | Alan Fogerty | Paul J | [5 empty] | Canada
|  |  | Boca Raton Regional Hospital | 5642173 | In Process | 2014-04-25 | 2014-11-01 |  | 2014-05-12 | 2015-04-07 |  |  | Customer | 17 | -41754 | 13000 | 1/12: trying to get wbex set up, will follow up for onsite date 1/16: offered Feb 11 or Apr 6 OS | Fla | US | VPM | QS OS |  | cindy | Paul J
|  | 180 | MANHATTAN-OGDEN PUBLIC SCHOOLS | 5705380 | Scheduled | 2015-01-16 |  | 2015-02-04 | 2015-02-06 | 2015-04-14 |  |  | Resource | 21 | -42020 |  | 2/3: intro email sent 2/6: scheduled | Manhattan, Ks | US | VPM | QS OS | Geoffrey Paul David O bill Wells | Cindy | Paul J
|  |  | Zebra |  | Scheduled |  |  |  |  | 4/7 4/14 |  |  | Standard |  |  |  | tentative AM-216 4/14 - approved 15% discount, no additional Peter schedule a meeting with Vangie AM-214 proposed 4/7 3/18: need PO by 3/20 & 3/23 |  |  | WLAN |  | Vangie
|  | HI HOLD | G6 HOSPITALITY LLC | 5701555 | Scheduled | 2014-12-31 | 2015-01-15 | 2015-02-11 | 2015-02-18 | 2015-04-21 |  |  | Standard | 49 | -42004 | 18000 | 5200 | TX | US | VPM | QS OS | Matt Marchbanks | Jerome | Paul J
|  |  | State of Alabama / Alabama ISD | 5687380 5687383 VSS | Scheduled | 2014-10-21 |  | 2014-11-12 | 11/13/14 2/23/15 | 2015-04-28 |  |  | Customer | #VALUE! | -41933 | 15300 | building DC, check in mid-Feb 2/18: customer is ready to restart, requested call for 2/23: reset call, Cindy will get them going | AL | US | VPM | QS OS | Adam Kurtz Douglas Jones Ray Feldman | Cindy | Paul J
private | ü |  | LAUSD | 5698456 5699085 | Complete | 2014-12-15 |  | 2014-12-15 | 2015-01-07 | 1/9/15 2/27/15 | 2015-02-28 | 2015-02-28 | Standard | 23 | 75 | 135000 | in process. 2 onsite visits scheduled 26-30-Jan and 23-27 Feb. 2-day Mar 23/24 | LA | US | VPM | QS OS | Mike Jett Trish Gundy | Dennis | Dennis
|  | Free | Teleus |  | Complete |  |  |  |  | 2/10 & 2/13 | [6 empty] | remote training for free | CA | US | WLAN |  | Arne Lepp
|  | 500 | Austal USA | 5696765 | In Process | 2014-12-04 |  |  | 2014-12-04 | 3/09 3/16 |  |  | Customer | 0 | -41977 | 50000 | 1/12: (NDA Douglas), Insurance (Scott) 1/21: checkin today 2/6: contractor training tues 530-830 will allow wits to not require an escort. Monday start. Graham will confirm dates with Jeff and Brice Monday (2/9) morning Dates confirmed 2/18: service agreement went to MK on the 9th, Wendy & Matt 3/25: waiting for report review date 4/1: reviewed 1st report. Revisions will be ready 4/6 as well as remaining reports. Schedule for next review is Tuesday 4/7 |  |  | WLAN
|  |  | Central Intelligence Agency | 5633554 | Booked | 2014-03-18 | 2014-11-01 | [5 empty] | Customer | -41716 | -41716 | 8840 | Sent information to Stephanie |  |  | WLAN
|  | rebooked | INGRAM MICRO (NESTLE USA) | 5614568 | Booked | 2013-12-23 | 2014-12-01 | [5 empty] | Customer | -41631 | -41631 | 14658.25 | 1/5: followed up w/customer 3/25: debooked |  |  | WLAN
|  | switched to credits 139 | TIME WARNER CABLE INC | 5679452 | Booked | 2014-06-27 | 2015-06-27 |  | 2015-02-25 | 2015-05-19 | 2015-05-21 |  | Customer | 243 | -41817 | 13882.5 | 9/23/14: closed HI HOLD/switched to credits. 1st or 2nd week of May - waiting to hear back from Gordon | TX |  | WLAN | AM214 w/exam
na | na | HI HOLD | Mary Kay | 5687831 | Complete | 2014-10-28 |  | 2014-10-25 | 2014-11-04 | 2015-03-24 |  | 2015-04-03 | Customer | 7 | 157 | 16500 | Pending second PO 1/14 follow up call 2/2: confirmation call • 3/24-3/26 - AM-214 3day training •TBD – 5day OJT (waiting PO and service agreement closure) 2/6: service agreement to be finalized with Anixter 3/24 scheduled for site survey |  |  | WLAN |  | Matt
|  | HI HOLD | NETCOM G5 OED IRON BOW TECHNOLOGIES | 5677423 | Complete | 2014-09-19 |  |  |  | 2015-02-26 | 2015-02-28 | 2015-02-24 | Standard | -41901 | 158 | 7000 |  |  |  | CSN |  |  | Uta | Pinacchi
| ü | 52 | Macys Rogue | 5700776 | Complete | 2014-12-23 |  |  |  |  | 2014-12-10 | 2015-12-10 | Standard | -41996 | 352 | 5200 |  | remote | US | WLAN |  | Lavonne |  | WITS
|  |  | TEKTRONIX S.A. DE C.V. | 30686789 | Complete | 2015-12-19 |  | 2015-01-21 | [5 empty] | -42357 | -42357 | 74442 | 1/14: contacted Jim Davis Francisco will deliver in 2 phases, brent is available to support if needed | Mexico | S. America | VPM | 2d CSN ASE Custom GEN (SOW) QS OS | Francisco Tarasuk,
|  | 150 | CETRA TECHNOLOGY INC ¦ FIDELITY CAPITAL | 5650425 | Booked | 2014-05-23 | 2015-05-23 | 2014-08-25 |  |  |  |  | Standard | -41782 | -41782 | 15000 | 2/2: cetra reached out to Dennis with an odd problem, requested feedback from Chris Greer | HI | US | VPM | QS Remote | Linda Ta | Dennis | na
|  | debooked | VERIZON COMMUNICATIONS INC | 5577778 | Complete | 2013-07-09 | [7 empty] | -41464 | -41464 | 35000 | Dave B, Jeff J and Peter need to close |  | other | VPM
|  | 150 | LSU HEALTH SCIENCES PRESIDIO NETWORKED SOLUTIONSCENTER | 5687192 | Booked | 2014-10-25 |  |  | 2014-12-09 |  |  |  | Customer | 45 | -41937 | 15000 | 10/27: requested info from David Oliver 11/12: email to customer 12/5: email to customer 12/9: contact them in mid-January | LO | US | VPM | QS Remote | David Oliver | Paul Z | na
|  | 140 | NV ENERGY Greybar | 5700406 | Booked | 2014-12-23 | [6 empty] | Standard | -41996 | -41996 |  |  |  | US | CSN
|  | 110 | SUMMIT MEDICAL GROUP PLLC AT&T CORPORATION | 5700417 | Booked | 2014-12-22 | 2015-12-29 | [5 empty] | Standard | -41995 | -41995 | 11000 | 1/15: David O sent intro, NEED TO FOLLOW UP | TN | US | VPM | QS Lite | David O Bill Wells | Sheldon |  | 4400-P
|  | 150 | SAFEWAY INC Accuvant | 5700988 | In Process | 2014-12-26 |  | 2015-01-09 | 2015-01-10 | 2015-01-15 |  |  | Standard | 15 | -41999 | 150000 |  | remote | US | VPM | QS Remote |  | Frank | na
|  | 70 | FIRST NATIONAL BANK OF FORT SMITH | 5700744 | Booked | 2014-12-23 |  |  | 2015-01-23 |  |  |  | Customer | 31 | -41996 | 7000 | 1/22: requested KO call 1/23? Follow up with Phil regarding OS 2/6: sent updated PP w/Brent as DP engineer. Requested follow call with customer to get QS going 2/12: no response from the customer to get started 3/26: RESTART - PAUL Z IS GETTING NOT RESPONSE | AK | US | VPM | 2day OS (?) | Matt David O Bill W | Paul Z | Brent
|  | 70 | NYSIF Anixter | 5703697 | In Process | 2015-01-14 | 1/23 2/3 |  | 2015-01-23 | 2015-01-28 |  |  | Customer | 9 | -42018 | 7000 | 1/21: requested KO call Barry install on 1/26-1/27 Sheldon provision 1/28 onsite not yet scheduled 3/26: checking in with Sheldon, the customer is moving really slowly. Estimated 2nd week of April | NY | US | VPM | QS Lite ASE install | Carl Kevin | Barry Sheldon
|  |  | Delta |  | Proposed |  |  |  | 2015-01-19 |  |  |  |  | 42023 | 0 |  | discovery call 1/12 & 1/16 |  | US | WLAN |  | Joe Woodwell
|  | HI HOLD | USAF Lockheed CO | 5705199 | Booked | 2015-01-15 | 2015-01-20 | [6 empty] | -42019 | -42019 |  | 1/15: Rick will send intro email to customer 2/3: followed up w/Rick | CO | US | VPM | QS OS | Rick Slominski Zack Belcher | Brent |  | 4800 w/XG
|  |  | Providence Health |  | Proposed | [8 empty] | 0 | 0 |  | 1/21: discovery call AM-215-day OJT in Seattle 4-6 people AM-214 3-day open enrollment |  |  | WLAN
|  | 150 | FMC TECHNOLOGIES INC | 5709048 | Scheduled | 2015-01-31 |  | 2015-02-20 | 2015-02-27 | 2015-04-20 | 2015-04-25 |  | Standard | 27 | -42035 | 15000 | 5-day XG training - checking with Peter to determine who can deliver Lisa will set up a kick off call about 3 weeks in advance of the class | Houston TX | US | WLAN | AM-211 OJT TRNPNA | Todd Davis?
|  | 180 | VON MAUR INC | 5708410 | Scheduled | 2015-01-29 |  | 2015-02-26 | 2015-02-26 | 2015-05-05 |  |  |  | 28 | -42033 |  | verify location will contact customer this week (2/12) 2/26:scheduled | IA | US | VPM | QS OS | GeoffreyPaul Stephen Davis | Sam O | Paul J
|  |  | IBM CANADA | 3541392 3541419 | Complete | [8 empty] | 0 | 0 | 5101 | Canada to deliver |  |  | WLAN | AM/S9200 AM/S9210
|  | 260 | Honeywell | 5724531 | Booked | 2015-04-02 |  |  |  | 2015-05-01 |  |  |  | -42096 | -42096 |  | update SOW, need PO# 3/11: checked in w/Chris for status 3/26: PO in hand, lisa will schedule a planning meeting |  |  | WLAN |  | Chris Wilson
|  |  | Hawaii Health |  | Proposed | [8 empty] | 0 | 0 |  | Pending Tax registration - HOLD off for merger or use a reseller. Scott to go direct, waiting to hear back from Linda Ta |  |  | WLAN |  | Linda Ta
|  | 150 | LIBERTY UNIVERSITY | 5712281 | Scheduled | 2015-02-12 | 2/27 3/15 | 2015-03-09 | 2015-03-11 | 2015-03-24 |  |  |  | 27 | -42047 | 15000 | 2/17: emailed Chuck and Jason for contact information and intro 2/23: contacted customer with welcome. Will send tracking information on 3/1 3/11: Chris Daniel will provide VOIP support. First Webext session scheduled to start 3/24 | VA | US | VPM | QS Remote | Chuck Smith Jason Cornwell | Sam O |  | VOIP
|  | 56 | LaSalle Solutions | 5722868 | Booked | 2015-03-27 |  |  |  | 2015-04-08 |  |  |  | -42090 | -42090 |  | 2/24: SOW proposed 3/11: followed/up 3/signed the SOW with added fee for LT travel |  |  | WLAN |  | Todd Davis?
|  | 180 | CENTER FOR DIAGNOSTIC IMAGING | 5717472 | In Process | 2015-03-04 | 2015-03-20 |  | 2015-04-07 |  |  |  |  | 34 | -42067 | 18000 | 5775 Wayzata Blvd Ste 190 ST LOUIS PARK, MN 55416 US | MN | US | VPM | QS OS | Steven Davis David Parker |  |  | 5200 w/taps
completed |  |  | AGILITY HOLDINGS INC | 5678192 | In Process | 2014-09-23 |  |  | 2014-09-30 | 2015-10-15 |  |  | Customer | 7 | -41905 |  | global distributed system first went to Irvin, CA for config then they shipped (Kuwait, Singapor, others) Phil had me close the QS in 2014. keep open for class registration for Vincent. He will let me know when they are ready 3/20: this is still in process |  | US | VPM | 4 seats to TV training | Michael Jett | Frank
|  | 44 | ST MARY'S UNIVERSITY | 5718959 | Booked | 2015-03-11 | [9 empty] | 4400 | 44 Training Credits to be used for these classes and secure AirMagnet Training Certification: AM-101 (18 credits) AM-214 (26 credits) |  |  | WLAN |  | Chris Wilson
|  | 140 | ACXIOM CORPORATION | 5718433 | Scheduled | 2015-03-10 |  |  |  | 2015-04-27 |  |  |  | -42073 | -42073 | 14000 |  |  |  | VPM | TV Class
|  | 180 | Bay District Schools | 5719583 | Scheduled | 2015-03-13 | 3/20 3/27 |  | 2015-04-01 | 2015-04-28 |  |  |  | 19 | -42076 |  | webex 1 4/14 | Fla | US | VPM | QS OS | Dave B Chuck Ray | Sam O | Dennis WiTs shadow | 6200 w/taps | Tom Molczynski tomm@wirelesstrainingsolutions.com (973) 531-7627 Jesse Hunton (404) 247-1352 jhunton@wirelesstrainingsolutions.com
|  |  | Canada Blood Services | 30744263 | Scheduled | 2015-03-16 | 2015-03-27 |  | 2015-03-20 | 2015-05-12 |  |  |  | 4 | -42079 |  | 3/16: PO in hand, with OE webex scheduled for 3/30 & 3/31 | Canada | US | VPM | QS OS | Arne | Sam O | Paul J | distributed
|  | 180 | State of Arizona Department of Economic Security | 5721337 | In Process | 2015-03-20 | 3/30 4/17 | 2015-04-02 | 2015-04-08 |  |  |  |  | 19 | -42083 |  | PO in hand 3/25: contacted with shipping and request for KO call | Az | US | VPM | QS OS VSS | Mike Jett Trish Gundy |  |  | 6200 w/XG
|  | 70 | SEATTLE CHILDREN'S HOSPITAL | 5719579 | Booked | 2015-03-16 | [10 empty] | I will ping Bonnie |  |  | WLAN |  | Bonnie
|  | 200 | TIME WARNER CABLE INC | 5723118 | Booked | 2015-03-31 |  |  |  | 2015-04-28 | 2015-04-30 |  |  |  |  | 15000 | 3-day onsite | NY | US | WLAN | AM-214 | Matt
|  |  | BERKLEY TECHNOLOGY SERVICES (Phase III) UK Install | 30746821 7082616 (-) | In Process | 2015-03-19 | 2015-04-10 |  | 2015-04-07 |  |  |  |  | 19 | -42082 |  | UK installation |  | EMEA | VPM | QS Remote | Carl Kevin | Frank
|  |  | BURLINGTON NORTHERN & SANTA FE RAILWAY COMPANY | 5722423 | Scheduled | 2015-03-25 |  | 2015-03-31 | 2015-04-02 | 2015-05-19 |  |  |  | 8 | -42088 |  | QuickStart is to address support for customization. They have 2 6200's and 2 4800's already installed | Fort Worth TX | US | VPM | QS OS | Matt Bill David O |  | Paul J | QuickStart is to address support for customization. They have 2 6200's and 2 4800's already installed
|  | 258 | Georgia Pacific | 5714231 | Complete | 2015-02-19 |  |  |  | 2015-03-09 | 2015-03-15 |  |  | -42054 | -42054 |  | 3/27: working to schedule a report date close out today . 4/2 |  |  | WLAN |  | Vangie
|  | 28 | Hillenbrand ¦ Batesville Services ¦ Batesville? | 5723011 | Booked | 2015-03-27 | [10 empty] | PO received 3/26. |  |  | VPM | 2 seats | david P
|  | 292 | Charles Schwab |  | Proposed | [11 empty] | 2015-03-27 |  |  | WLAN | AM211 OJT | Chris Wilson
|  | 70 | CARNIVAL CRUISE LINE | 5642240 | Booked | 2015-03-26 | [10 empty] | 2day? |  |  | CSN
|  | 180 | TRANSFIRST LLC | 5723113 | Booked | 2015-03-26 | [9 empty] | 18000 |  | Irvine CA or CO | US | VPM | QS OS | Michael Jett Trish Gundy |  |  | 6200 (2)
|  |  | Parker.com |  | Proposed | [11 empty] | 2015-04-01 |  |  | WLAN |  | David Walker
|  | 375 | State of Arizona Department of Economic Security | 5721337 | In Process | 2015-03-20 |  | 2015-04-02 | 2015-04-08 | [8 empty] | Az | US | VPM | 1/4ly health checks | Michael Jett Trish Gundy

## TVEndUser
| Start Date | End Date | Enroll | Link
| 2015-02-11 | 2015-02-12 | 1 Summitt Electric - sent reg 1/5 2 MIAMI-DADE - sent 1/5 2 Agility - 1 2 Jacob Javits - sent 1/5 2 Buckeye Partners - sent 1/5 2 ANHEUSER-BUSCH - sent 1/5 2 ATT Trade Bureau - sent 1/5 3 Middlesex - waiting for PO to cover 3rd 2-Scottsdale Health 2/23 | https://ywcsolutions.infusionsoft.com/app/form/fluke-networks-truview-2day-registration
| 2015-03-26 | 2015-03-27
remote | 4/20/2015 R | 2015-04-21
remote | 2015-05-06 | 2015-05-07
in person | 2015-06-11 | 2015-06-12

## QS Time To Fulfill
All
2014 |  | Target | Book to KO (Avg) | 2015
Jan | 106 | 60 |  | 48
Feb | 70 | 60 |  | 89
Mar | 96 | 60 | 20.5 | 110
Apr | 96 | 60 | 13
May | 86 | 60 | 16
Jun | 49.33 | 60 | 21
Jul | 49 | 60 | 29
Aug | 57 | 60 | 40
Sep | 241 | 60 | 19
Oct | 111 | 60 | 21
Nov | 42 | 60 | 32
Dec | 119 | 60 | 56
total Avg | 93.5275 |  | 26.75
Standard
2014 |  | Target | 2015
Jan | 57.6 | 60 | 48
Feb | 70.3 | 60 | 65
Mar | 33 | 60 | 0
Apr | 33 | 60
May | 41.5 | 60
Jun | 49 | 60
Jul | 49 | 60
Aug | 51 | 60
Sep | 29 | 60
Oct | 52 | 60
Nov | 42 | 60
Dec | 56 | 60
total Avg | 46.95
Customer
2014 |  | Target | 2015C | 2015R
Jan | 167.3 | 60 | 48
Feb | 0 | 60 | 231
Mar | 86 | 60 | 129 | 97
Apr | 154.6 | 60
May | 137 | 60
Jun | 72 | 60
Jul | 0 | 60
Aug | 78 | 60
Sep | 326 | 60
Oct | 152 | 60
Nov | 0 | 60
Dec | 188 | 60
total Avg | 113.4083

## QS Backlog Totals
| delivered | booked
2011 | 10
2012 | 38 | 38
2013 | 30 | 57
2014 | 64 | 86
2015 | 5 | 4
2014 | backlog | booked | delivered
Jan | 25 | 3 | 6
Feb | 22 | 5 | 3
Mar | 24 | 6 | 9
Apr | 21 | 6 | 12
May | 15 | 5 | 6
Jun | 14 | 6 | 4
Jul | 16 | 5 | 3
Aug | 18 | 1 | 7
Sep | 12 | 8 | 5
Oct | 15 | 5 | 4
Nov | 16 | 2 | 2
Dec | 16 | 16 | 9
|  | 68 | 70
2015 | backlog | booked | delivered | in process
Jan | 23 | 4 | 5
Feb | 26 | 1 | 5 | 14
Mar | 4 | 8 | 10 | 11
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec

## Resource
| Onsite | Remote
TAC | 4 | 13
Partner | 8 | 0
PS | 0 | 3
Unscheduled | 5 | 1
| TAC | Partner | PS
Feb | 20 | 8 | 3
Mar | 8 | 8 | 4
Apr
May
Jun
Jul
Aug
Sep

## class bookings
FNET Geography | Sales Agent Name | Activity Yr | Activity Mo No | Activity Date | BT Customer Name | Order No | Customer PO Ref | ST Customer Name | ST State/Province Code | ST City | ST Postal Code | ST Country Name | Product Family Code | Model Group Code | Item No | Model | Forecast Group Code | Item Desc | Ordered Qty | Net USD | List USD (US Price List)
USA | AirMag ISR - Wilson - Filer | 2015 | 3 | 2015-03-24 | QWEST COMMUNICATIONS | 5722384 | 180746 | QWEST COMMUNICATIONS | CO | Frederick | 80530 | United States | WLAN | TRNWL | 3536005 | AM/AM-214 | WLMOBILE | AM/AM-214,AIRMAGNET 3-DAY ADVANCED WLAN DESIGN AND SITE SURVEY CLASS | 1 | 2545 | 2545
USA | AirMag ISR - Sobrepena - Woodwell | 2015 | 3 | 2015-03-26 | INGRAM MICRO | 5722870 | 07-77620 | HEARTLAND COMPUTERS INC | IL | MCHENRY | 60050 | United States | WLAN | TRNWL | 4545334 | SVS-WLAN-CRMOB | WLMOBILE | SVS-WLAN-CRMOB,CREDITS - 1 = 00 FOR TRAINING/SERVICES | 26 | 2210 | 2600
USA | AirMag ISR - Velez | 2015 | 3 | 2015-04-01 | LORD ABBETT & CO LLC | 5724360 | 231225/8675 | LORD ABBETT & CO LLC | NJ | JERSEY CITY | 7302 | United States | WLAN | TRNWL | 4545334 | SVS-WLAN-CRMOB | WLMOBILE | SVS-WLAN-CRMOB,CREDITS - 1 = 00 FOR TRAINING/SERVICES | 26 | 2600 | 2600
[5 empty] | Phillips | 5707057 |  | Phillips | [10 empty] | 156 | 15600 |  | 7800 | 7800
[6 empty] | 5717520 | [12 empty] | 26 | 2600
[6 empty] | 5689443 | [12 empty] | 26 | 2600